# Tab 1

# Mobile Banking Application Project Case Study

# Case Study Narrative

Assume the role of a project manager working alongside members of a large bank's Project Management Office (PMO). The team has been tasked with developing a mobile banking application that allows users to perform banking transactions, view account balances, transfer money, pay bills, enhance customer convenience, and reduce operational costs.

# Project Overview

- Project Name: Development of a Mobile Banking Application

- Objectives:

  - Enable users to perform banking transactions

  - View account balances

  - Transfer money and pay bills

  - Enhance customer convenience and reduce operational costs

- Expected ROI: 25% within two years

- Initial Investment: $500,000

- Project Duration: 12 months

- Estimated Financial Benefits:

  - Revenue: $200,000 per year

  - Savings: $50,000 per year

# Original Baselines

## Scope Baseline

- Fully functional mobile banking app with core banking features

- Integration with existing banking systems

## Schedule Baseline

| Phase | Duration |
| --- | --- |
| Planning | 1 month |
| Development | 6 months |
| Testing | 3 months |
| Deployment | 2 months |
| Total Duration | 12 months |

## Cost Baseline

| Phase | Estimated Cost |
| --- | --- |
| Planning | $50,000 |
| Development | $300,000 |
| Testing | $100,000 |
| Deployment | $50,000 |
| Total Cost | $500,000 |

# Updated Baselines

After 6 months, additional security features were required due to new regulatory requirements.

## Updated Scope

- Includes additional security features

## Updated Schedule

| Phase | Revised Duration |
| --- | --- |
| Planning | 1 month |
| Development | 8 months (extended by 2 months) |
| Testing | 3 months |
| Deployment | 2 months |
| Total Duration | 14 months |

## Updated Cost

| Phase | Estimated Cost |
| --- | --- |
| Planning | $50,000 |
| Development | $400,000 (increased by $100,000) |
| Testing | $100,000 |
| Deployment | $50,000 |
| Total Cost | $600,000 |

# Important Project Notes

Experts warn that if the security feature is not included, there is a 90% probability of a severe threat with an impact of $80,000. If included, the risk reduces to a 5% probability with an impact of $6,000.

The revised development duration was validated using PERT (Program Evaluation and Review Technique):

- Optimistic (O): 7 months

- Most Likely (ML): 8 months

- Pessimistic (P): 9 months

- Expected Duration (E): (O + 4*ML + P) / 6 = (7 + 4*8 + 9) / 6 = (7 + 32 + 9) / 6 = 48 / 6 = 8 months